## Requirement Overview
Project Name | Crime Rate Analysis in Toronto | Date | 2023-12-08 |  | Group #03 | Team Members
Project Number | # 03 | Document Number |  |  | Srilakshmi Gummadidala: 0803509
Project Manager | Harpreet Virk | Project Owner/Client |  |  | Yen Nga Le: 0824817
Tehsin Shaikh:0831234
Vinod Soloman Santhakumar: 0821990
ACTION | DESCRIPTION | PRIORITY | PROGRESS | STATUS | APPROVAL STATUS | END DATE
Project Initiation
Define Project Objectives | Project's overarching goals and intended outcomes | High | 100% | COMPLETED | APPROVED | 2023-11-03
Identify Key Stakeholders | Individuals or groups who interested or influenced in the project's success.Ex. Project Sponser,Customer etc. | High | 100% | COMPLETED | APPROVED | 2023-11-03
Conduct Stakeholder meetings and Analysis | Organize meetings to engage stakeholders | Medium | 100% | COMPLETED | APPROVED | 2023-11-10
Develop Project Charter | Comprehensive document outlining the project's objectives, scope, stakeholders, constraints, and key deliverables. | High | 100% | COMPLETED | APPROVED | 2023-11-03
Prepare Business Case | A detailed rationale, including cost estimation and benefits analysis | High | 100% | COMPLETED | APPROVED | 2023-11-03
Project Planning
Define Scope and Deliverables | Outline the project's boundaries, objectives, and expected outcomes | High | 100% | COMPLETED | APPROVED | 2023-11-17
Develop Project Schedule | A roadmap for successful project execution | Medium | 100% | COMPLETED | APPROVED | 2023-11-17
Create Work Breakdown Structure (WBS) | Project tasks and structure for effective planning and execution. | High | 100% | COMPLETED | APPROVED | 2023-11-17
Resource Planning | Allocation and managining of project resources for optimal utilization. | Medium | 100% | COMPLETED | APPROVED | 2023-11-24
Risk Identification and Analysis | Identifying potential risks and analyze their impact | High | 100% | COMPLETED | APPROVED | 2023-11-24
Budgeting and Cost Estimation | Estimation of financial requirements for project execution | High | 100% | COMPLETED | APPROVED | 2023-11-24
Quality Planning | Define processes and standards to ensure project deliverables meet quality expectations | Medium | 100% | COMPLETED | APPROVED | 2023-11-24
Communication Planning | Strategies for effective communication within the project team and stakeholders | Medium | 100% | COMPLETED | APPROVED | 2023-11-24
Approval and Baseline | Approval for project plans and establish a baseline for project execution. | High | 100% | COMPLETED | APPROVED | 2023-11-24
Requirements Collection and Analysis
Identify Data Sources | Identify and document the sources from which data will be collected for the project | High | 100% | COMPLETED | APPROVED | 2023-12-01
Data Collection and Analysis | Collect and analyze project data for meaningful insights | Medium | 100% | COMPLETED | APPROVED | 2023-12-01
Review Existing Crime Databases | Assess and evaluate the current crime databases for review and improvement | Medium | 100% | COMPLETED | APPROVED | 2023-12-01
Establish Data Collection Protocols | Establish protocols for systematic data collection | Medium | 75% | IN PROGRESS | APPROVED | 2023-12-01
Implement Models for Crime Data Analysis | Implement analytical models for in-depth crime data analysis. | High | 25% | ON HOLD | NEEDS APPROVAL | 2024-01-26
Deploying Machine Learning Models | Models for practical application and real-time usage | High | 10% | ON HOLD | NEEDS APPROVAL | 2024-01-26
Monitor Data Quality and Risk Response | Continuously monitor data quality and assess risk response strategies | High | 50% | IN PROGRESS | APPROVED | 2024-01-26
Implement Mitigation and Contingency plans | Plans to address identified risks effectively | High | 25% | IN PROGRESS | NEEDS APPROVAL | 2024-01-26
Requirements and Justification
Functional Requirements | Essential system functions to meet project goals and stakeholder requirements | High | 100% | COMPLETED | APPROVED | 2023-12-01
Non - Functional Requirements | System performance, security, usability, and other non-functional aspects. | High | 100% | COMPLETED | APPROVED | 2023-12-01
Business Requirements | Functionalities and features needed to address business goals and objectives | Medium | 75% | IN PROGRESS | NEEDS APPROVAL | 2023-02-23
Operational Requirements | System requirements for effective operation and maintenance | Medium | 50% | IN PROGRESS | NEEDS APPROVAL | 2023-02-23
Stakeholder Requirements | Incorporate stakeholder needs and expectations into project deliverables | Medium | 50% | IN PROGRESS | NEEDS APPROVAL | 2023-02-23
Other Ethical & Future Requirements | Ethical considerations and plan for future requirements | Medium | 20% | IN PROGRESS | NEEDS APPROVAL | 2023-02-23
Summary Reports
Scope & Context | Outlining the overall objectives and boundaries | High | 100% | COMPLETED | APPROVED | 2023-12-08
Design Goals | Description of the design goals for the project, including key features | High | 75% | IN PROGRESS | APPROVED | 2023-12-08
Team & Resources | Overview of the project team structure, roles, and allocation of resources | Medium | 75% | IN PROGRESS | APPROVED | 2023-12-08
Summary Timeline | A concise timeline outlining key milestones and deadlines | Medium | 100% | COMPLETED | APPROVED | 2023-12-08

## Requirement Matrix
Requirement ID | Requirement | Priority | Category | Source | WBS Code | Verification | Validation
REQ-01 | Project Objectives | High | Mandatory | https://data.torontopolice.on.ca/ | 1.1 | Project Team/Sponser | Sponser
REQ-02 | Data Collection and Analysis | Medium | Mandatory | https://data.torontopolice.on.ca/ | 4.1 | Project Team | Sponser
REQ-03 | Review Existing Crime Databases | Medium | Should have | NA | 4.1.3 | Project Team | Sponser
REQ-04 | Establish Data Collection Protocols | Medium | Should have | Tableau, Python | 4.1.2 | Project Team | Sponser
REQ-05 | Implement Models for Crime Data Analysis | High | Mandatory | NA | 4.2 | Project Team | Sponser
REQ-06 | Deploying Machine Learning Models | High | Mandatory | NA | 5.1 | Project Team | Sponser
REQ-07 | Monitor Data Quality and Risk Response | Medium | Should have | NA | 6.1 | Project Team | Sponser
REQ-08 | Implement Mitigation and Contingency plans | High | Mandatory | NA | 6.4 | Project Team | Sponser
REQ-09 | Future Enhancements | Low | Nice to Have | NA | 6.3 | Project Team | Sponser