## RACI Matrix
RACI MATRIX |  |  |  | R | Responsible |  |  |  | A | Accountable |  |  |  | C | Consulted |  |  |  | I | Informed
|  | Executive Sponsor | Project Sponsor | Faculty Advisor | Professor/Mentor | Quality Assurance Manager | Project Manager | Team Lead | Data Analyst | Machine Learning Engineer | Project Team Manager | Dashboard Developer | Reporting Specialist | Business Analyst | Administrative Support | Visualization Expert | Classmates and Peers | College Administrative Support | Law Enforcement Department | Community Members | Ethical and Privacy Experts
Status | Project Deliverables/ Activity | Project Leadership |  |  |  |  | Project Team Members |  |  |  |  | Project Sub-Teams |  |  |  |  | External Resources
PROJECT INITIATION
Completed | Define Project Objectives | A | A | A | C | C | R | R | C | C | R | C | C | C | I | C | I | I | C | C | C
Completed | Identify Key Stakeholders | bar: A to R; R to C; C; C to C
Completed | Conduct Stakeholder meetings and Analysis | bar: A to R; R to C; C
Completed | Develop Project Charter | A: A; A: A; A: C; C: C; C: A; R: R; R: C; C: C; R: R; C: C
Completed | Prepare Business Case | A | A | C | C | A | R | R |  |  | R |  |  | C |  |  |  |  | C | C | C
Completed | PROJECT PLANNING
Completed | Initiate Project Planning Phase | A: A; A: A; A: C; C: C; R: R; R: C; R: R; C: C
Completed | Define Scope and Deliverables | A: A; C: C; C: C; R: R; R: R; C: C; C: I; C: I; C: I
Completed | Create Work Breakdown Structure (WBS) | A: A; A: A; A: A; C: C; C: A; R: R; R: C; R: C; C: C
Completed | Develop Project Schedule | A: A; A: A; A: A; C: C; C: A; R: R; R: C; C: C; C: C; R: R; C: C
Completed | Resource Planning | C | A | A | A | A | R | R | C | C | R | C | C | C | C | C | I | C
Completed | Risk Identification and Analysis | A | A | A | C | A | R | R | R | R | R | C | R | R | C | C | I | C | C | C | C
Completed | Budgeting and Cost Estimation | C A: C; A A: A; A C: C; A A: C; R R: R; R R: C; C C: C
Completed | Quality Planning | bar: C A to C R; C C
Completed | Communication Planning | C A: I; A A: I; A A: I; A C: I; R R: R; R R: C; R R: C; C R: C; C R: C
Completed | Approval and Baseline | C A: A; A A: A; A A: I; A C: C; A A: C; R R: R; R R: R; R R: R; C R: C
PROJECT EXECUTION
Completed | Data Collection and Analysis | A A: C; A C: C; R R: A; C R: R; C R: R; C C: C; C R: R; C C: C
Completed | Reporting and Visualization | bar: C A to C R; C C
In Progress | Implement Machine Learning Models for Crime Data Analysis | bar: C A to C R; C C
In Progress | Monitor Data Quality and Risk Response | A A: A; R R: R; R R: R; C R: R; C R: C; R R: A; C C: C; C R: C; C R: R; C C: C
MONITORING AND CONTROLLING
In Progress | Continuous Monitoring and Evaluation | bar: C A to C R; C C
Not Started | Feedback and Iterative Improvement | bar: C A to C R; C C
In Progress | Change Control and Approval Process | C A: I; A A: A; A A: C; A C: C; A A: A; R R: A; R R: R; R R: R; C R: C
In Progress | Control Scope and Costs | C A: A; A A: A; A A: C; A C: C; A A: R; R R: R; R R: C; R R: C; C R: C
In Progress | Control Quality and Resources | A A: I; A A: A; R R: R; R R: C; R R: R
In Progress | Monitor Risks & Risk Response Evaluation | R R: R; C R: R; C R: C; R R: A; C R: C; C R: R
In Progress | Communications and Procurement Control | A A: A; R R: R; R R: C; R R: R; C R: C
PROJECT CLOSING
In Progress | Final Reporting and Documentation | A A: A; A C: C; A A: C; R R: R; R R: R; C R: R; C R: C; R R: R; C R: C; I I: I
Not Started | Lessons Learned |  |  |  |  | A | R | R | R | R | R | R | R | R | C | R | I
Not Started | Handover to Stakeholders |  |  | A |  | A: A; R: R; R: R; R: R; R: C
Not Started | Project Sign-off and Closure | I | I | A | [13 empty] | I | bar: A to I

## Sheet1
RACI KEY |  | PRIORITY | STATUS
R | Responsible | Low | Not Started
A | Accountable | Medium | In Progress
C | Consulted | High | Completed
I | Informed |  | Needs Review
Approved
Overdue
On Hold
Responsible (R): Does the work.
Accountable (A): Makes the final decision and ensures the work gets done.
Consulted (C): Provides input and expertise.
Informed (I): Receives updates after the task is completed.