## Sheet1
Group No: #03
Team Members:
Srilakshmi Gummadidala: 0803509
Yen Nga Le: 0824817
Tehsin Shaikh:0831234
Vinod Soloman Santhakumar: 0821990
WBS Code | Project Task/Action | Priority | Start Date | End Date | Duration in Days | Assigned Team | % of Completion | Allocated Hours
1 | PROJECT MANAGEMENT | High | 2023-10-05 | 2023-11-05 | 31 | Project Manager, Project Team | 100 | 132
1.1 | Project Initiation | High | 2023-10-05 | 2023-10-08 | 3 | Project Manager, Project Team | 100 | 16
| Define Project Scope/Objectives | High | 2023-10-05 | 2023-10-06 | 1 | Project Manager, Project Team | 100 | 8
| Identify Key Stakeholders | Medium | 2023-10-06 | 2023-10-07 | 1 | Project Manager, Project Team | 100 | 8
| Define Project Requirements | Medium | 2023-10-07 | 2023-10-08 | 1 | Project Manager, Project Team | 100 | 8
| Define Cost and Budgeting | High | 2023-10-07 | 2023-10-08 | 1 | Project Manager, Project Team | 100 | 8
1.2 | Project Planning | High | 2023-10-08 | 2023-10-12 | 4 | Project Manager, Project Team | 100 | 32
| Define Scope and Deliverables | High | 2023-10-08 | 2023-10-09 | 1 | Project Manager, Project Team | 100 | 8
| Create Work Breakdown Structure (WBS) | High | 2023-10-09 | 2023-10-11 | 2 | Project Manager, Project Team | 100 | 12
| Develop Project Schedule | Medium | 2023-10-11 | 2023-10-12 | 1 | Project Manager, Project Team | 100 | 8
| Resource Planning | Medium | 2023-10-11 | 2023-10-12 | 1 | Project Manager, Project Team | 100 | 8
| Budgeting and Cost Estimation Planning | High | 2023-10-11 | 2023-10-12 | 1 | Project Manager, Project Team | 100 | 4
1.3 | Project Tracking | High | 2023-10-12 | 2023-10-15 | 3 | Project Manager, Project Team | 100 | 12
| Conduct Stakeholder meetings | Medium | 2023-10-12 | 2023-10-13 | 1 | Project Manager, Project Team | 100 | 8
| Regularly Review Project Scope/Progress | Medium | 2023-10-12 | 2023-10-13 | 1 | Project Manager, Project Team | 100 | 8
| Communicate Changes to Stakeholders | Medium | 2023-10-13 | 2023-10-15 | 2 | Project Manager, Project Team | 100 | 8
1.4 | Risk Analysis Management | High | 2023-10-15 | 2023-10-21 | 6 | Project Manager, Project Team | 75 | 8
| Identify Risks | High | 2023-10-15 | 2023-10-17 | 2 | Project Manager, Project Team | 75 | 4
| Assess Impact of Risks | High | 2023-10-17 | 2023-10-20 | 3 | Project Manager, Project Team | 75 | 4
| Develop Risk Register | Medium | 2023-10-20 | 2023-10-21 | 1 | Project Manager, Project Team | 75 | 8
1.5 | Quality Management | Medium | 2023-10-21 | 2023-10-26 | 5 | Project Manager, Project Team | 75 | 32
| Define/Monitor Quality Standards | Medium | 2023-10-21 | 2023-10-24 | 3 | Project Manager, Project Team | 75 | 4
| Identify Quality Assurance Measures | Medium | 2023-10-22 | 2023-10-25 | 3 | Project Manager, Project Team | 75 | 8
| Create Quality Management Plan | Medium | 2023-10-23 | 2023-10-26 | 3 | Project Manager, Project Team | 75 | 12
1.6 | Change Management | Medium | 2023-10-26 | 2023-11-05 | 10 | Project Manager, Project Team | 50 | 40
| Identify Changes | Low | 2023-10-26 | 2023-10-30 | 4 | Project Manager, Project Team | 50 | 16
| Validate Changes and impact | Medium | 2023-10-31 | 2023-11-02 | 2 | Project Manager, Project Team | 50 | 4
| Get Approvals for Changes | Medium | 2023-11-02 | 2023-11-04 | 2 | Project Manager, Project Team | 50 | 8
| Communicate& Document Changes | Medium | 2023-11-04 | 2023-11-05 | 1 | Project Manager, Project Team | 50 | 8
2 | PROJECT REQUIREMENTS | High | 2023-11-05 | 2023-12-05 | 30 | Project Team | 100 | 120
2.1 | Requirement Collection | High | 2023-11-05 | 2023-11-17 | 12 | Project Team | 100 | 48
| Define Scope Requirements | High | 2023-11-05 | 2023-11-08 | 3 | Project Team | 100 | 8
| Collect Data Requirements | Medium | 2023-11-08 | 2023-11-13 | 5 | Project Team | 100 | 4
| Analyse Requirements | Medium | 2023-11-13 | 2023-11-17 | 4 | Project Team | 100 | 12
2.2 | Requirement Analysis | Medium | 2023-11-17 | 2023-11-26 | 9 | Project Team | 100 | 52
| Review Requirements | Low | 2023-11-17 | 2023-11-23 | 6 | Project Team | 100 | 24
| Validate Requirements | High | 2023-11-23 | 2023-11-24 | 1 | Project Team | 100 | 8
| Get Approval for Changes | High | 2023-11-24 | 2023-11-25 | 1 | Project Team | 100 | 8
| Apply changes and Document | Medium | 2023-11-25 | 2023-11-26 | 1 | Project Team | 100 | 8
2.3 | Requirement Testing | High | 2023-11-26 | 2023-12-05 | 9 | Project Team, Testing Team | 100 | 16
| Test Requirements | High | 2023-11-26 | 2023-11-29 | 3 | Project Team, Testing Team | 100 | 15
| Communicate Test Results | Medium | 2023-11-29 | 2023-12-01 | 2 | Project Team, Testing Team | 100 | 8
| Get Feedback from Stakeholders | Medium | 2023-11-29 | 2023-12-01 | 2 | Project Team | 100 | 8
3 | PROJECT DESIGN | High | 2023-12-05 | 2024-01-08 | 34 | Development Team | 100 | 16
3.1 | System Architecture Design | High | 2023-12-05 | 2023-12-19 | 14 | Development Team | 100 | 12
| Define High-level Architecture | High | 2023-12-09 | 2023-12-19 | 10 | Development Team | 100 | 4
| Define System Requirements | High | 2023-12-09 | 2023-12-12 | 3 | Development Team | 100 | 16
| Design Technical Specifications | High | 2023-12-09 | 2023-12-11 | 2 | Development Team | 100 | 8
| Develop Data Models | Medium | 2023-12-09 | 2023-12-12 | 3 | Development Team | 100 | 8
3.2 | Detailed Technical Design | Medium | 2023-12-05 | 2023-12-13 | 8 | Development Team | 100 | 168
| Develop Detailed Technical System | Medium | 2023-12-05 | 2023-12-13 | 8 | Development Team | 100 | 8
| Develop Network Diagrams | Medium | 2023-12-05 | 2023-12-06 | 1 | Development Team | 100 | 8
3.3 | User Interface (UI) Design | High | 2023-12-05 | 2023-12-17 | 12 | Development Team | 100 | 40
| Develop Visual User interface | High | 2023-12-05 | 2023-12-17 | 12 | Development Team | 100 | 16
| Layout and Navigation Design | Medium | 2023-12-05 | 2023-12-07 | 2 | Development Team | 100 | 4
| Develop interactive Dashboards | High | 2023-12-05 | 2023-12-07 | 2 | Development Team | 100 | 16
| Develop feedback user interactions | Medium | 2023-12-06 | 2023-12-08 | 2 | Development Team | 100 | 28
3.4 | Test Plans | High | 2023-12-20 | 2024-01-08 | 19 | Development Team | 100 | 12
| Conduct Real user Testing | High | 2023-12-20 | 2023-12-26 | 6 | Development Team | 100 | 8
| Refine the Design based on Feedback | Medium | 2023-12-20 | 2023-12-23 | 3 | Development Team | 100 | 4
| Identify Potential Risks | High | 2023-12-21 | 2024-01-04 | 14 | Development Team | 100 | 8
| Outlines the Mitigation Plans | Medium | 2023-12-25 | 2023-12-27 | 2 | Development Team | 100 | 12
4 | DEVELOPEMENT AND VALIDATION | High | 2024-01-08 | 2024-02-08 | 31 | Development Team | 50 | 4
4.1 | Data Collection and Analysis | Medium | 2024-01-08 | 2024-01-16 | 8 | Development Team | 100 | 16
| Identify Data Sources | High | 2024-01-08 | 2024-01-10 | 2 | Development Team | 100 | 76
| Establish Data Collection Protocols | Medium | 2024-01-08 | 2024-01-10 | 2 | Development Team | 100 | 64
| Collect Historical Crime Data | Medium | 2024-01-08 | 2024-01-10 | 2 | Development Team | 100 | 4
| Write Code&Analyze Crime Trends | High | 2024-01-13 | 2024-01-16 | 3 | Development Team | 100 | 8
4.2 | Testing Code and Reporting | High | 2024-01-16 | 2024-01-27 | 11 | Development Team | 10 | 8
| Develop a comprehensive test plan | High | 2024-01-18 | 2024-01-27 | 9 | Development Team | 10 | 16
| Create Detailed Test Cases | Medium | 2024-01-17 | 2024-01-23 | 6 | Development Team | 10 | 8
| Execute Test Code | Medium | 2024-01-16 | 2024-01-25 | 9 | Development Team | 10 | 8
| Report Results and Track Defects | Medium | 2024-01-16 | 2024-01-19 | 3 | Development Team | 10 | 8
4.3 | Validate Code and Reporting | High | 2024-01-17 | 2024-02-08 | 22 | Development Team | 10 | 8
| Perform Validation on Validation Data | High | 2024-01-19 | 2024-02-08 | 20 | Development Team | 10 | 4
| Execute Validation Code | High | 2024-01-21 | 2024-02-03 | 13 | Development Team | 10 | 4
| Report Results and Track Defects | Medium | 2024-01-22 | 2024-02-04 | 13 | Development Team | 10 | 8
5 | DEPLOYMENT AND EVALUATION | High | 2024-02-08 | 2024-03-08 | 29 | Development Team | 0 | 120
5.1 | Deploying Machine Learning Models | High | 2024-02-08 | 2024-02-18 | 10 | Development Team | 0 | 12
| Select Deployment Environment | Medium | 2024-02-10 | 2024-02-15 | 5 | Development Team | 0 | 8
| Integrate Models into Crime Analysis | Medium | 2024-02-09 | 2024-02-18 | 9 | Development Team | 0 | 8
| Conduct Model Testing | High | 2024-02-12 | 2024-02-18 | 6 | Development Team | 0 | 8
5.2 | Deployment of Dashboards | High | 2024-02-18 | 2024-02-27 | 9 | Development Team | 0 | 16
| Data Source Connection to Dashboards | Medium | 2024-02-18 | 2024-02-27 | 9 | Development Team | 0 | 8
| Deploy Dashboard User Interface | Medium | 2024-02-18 | 2024-02-27 | 9 | Development Team | 0 | 8
| Optimize Dashboard Performance | Low | 2024-02-18 | 2024-02-27 | 9 | Development Team | 0 | 12
| Security & Access Controls | High | 2024-02-18 | 2024-02-27 | 9 | Development Team | 0 | 4
5.3 | User Testing & Trainings | Low | 2024-02-27 | 2024-03-08 | 10 | Testing Team | 0 | 4
| Perform User Testing | Low | 2024-03-02 | 2024-03-08 | 6 | Testing Team | 0 | 8
| Provide training to end-users | Low | 2024-03-02 | 2024-03-08 | 6 | Project Team, Testing Team | 0 | 4
| Document Deployment changes | Medium | 2024-03-03 | 2024-03-04 | 1 | Project Team, Testing Team | 0 | 4
| User Feedback Analysis | Medium | 2024-03-02 | 2024-03-05 | 3 | Project Team | 0 | 16
| Implement version control | Medium | 2024-03-02 | 2024-03-06 | 4 | Backup Team | 0 | 8
| Backup and Recovery Plan | High | 2024-03-02 | 2024-03-08 | 6 | Backup Team | 0 | 8
6 | SUPPORTING ACTIVITIES | Medium | 2024-03-08 | 2024-04-15 | 38 | Monitoring Team | 0 | 8
6.1 | Monitoring and Performance Analysis | Medium | 2024-03-08 | 2024-03-18 | 10 | Monitoring Team | 0 | 4
| Implement Monitoring tools | Medium | 2024-03-09 | 2024-03-18 | 9 | Monitoring Team | 0 | 4
| Analyze Metrics Regularly | High | 2024-03-08 | 2024-03-15 | 7 | Monitoring Team | 0 | 8
| Identify Areas of Improvement | Medium | 2024-03-08 | 2024-03-16 | 8 | Monitoring Team | 0 | 40
6.2 | Bug Fixes and Patches | High | 2024-03-18 | 2024-03-23 | 5 | SME, Development Team | 0 | 4
| Address reported bugs by bug fixes and Patches | High | 2024-03-18 | 2024-03-20 | 2 | SME, Development Team | 0 | 4
| Maintain a version control system | Medium | 2024-03-18 | 2024-03-23 | 5 | SME, Development Team | 0 | 4
| Track Changes which applied during Patches | Medium | 2024-03-20 | 2024-03-23 | 3 | SME, Development Team | 0 | 8
6.3 | Security Audits and Enhancements | Medium | 2024-03-23 | 2024-03-28 | 5 | Security Team | 0 | 4
| Conduct regular security audits | Medium | 2024-03-23 | 2024-03-25 | 2 | Security Team | 0 | 4
| Identify Vulnerabilities | Medium | 2024-03-23 | 2024-03-26 | 3 | Support Team, SME | 0 | 12
| Gather Feature Enhancement | Low | 2024-03-23 | 2024-03-24 | 1 | Support Team, SME | 0 | 4
| Analyse Enchancements and Design | Medium | 2024-03-25 | 2024-03-28 | 3 | Support Team, SME | 0 | 4
| Test & Deploy Enchancements | Medium | 2024-03-25 | 2024-03-28 | 3 | Support Team, SME | 0 | 2
6.4 | Performance Tuning | High | 2024-03-28 | 2024-04-05 | 8 | Support Team, SME | 0 | 4
| Performance Metrics Monitoring | Medium | 2024-03-29 | 2024-04-04 | 6 | Support Team, SME | 0 | 2
| Identify Bottlenecks | High | 2024-03-28 | 2024-04-03 | 6 | Support Team, SME | 0 | 4
| Optimization Strategies | High | 2024-03-30 | 2024-04-02 | 3 | Support Team, SME | 0 | 8
| Ethical and Legal Considerations | Medium | 2024-03-28 | 2024-04-05 | 8 | Support Team | 0 | 24
6.5 | Project Sign-off and Closure | High | 2024-04-05 | 2024-04-15 | 10 | Project Team, Project Manager | 0 | 12
| Go-Live with Production | High | 2024-04-05 | 2024-04-10 | 5 | Project Team, Project Manager | 0 | 12
| Prepare Formal Request for Project Sign-off | Medium | 2024-04-10 | 2024-04-12 | 2 | Project Team, Project Manager | 0 | 2
| Submit Sign-off Request to Key Stakeholders | Medium | 2024-04-12 | 2024-04-15 | 3 | Project Team, Project Manager | 0 | 4
| Obtain Formal Sign-off from Stakeholders | Medium | 2024-04-12 | 2024-04-15 | 3 | Project Team, Project Manager | 0 | 2
| Final Deliverables & Project Closure | High | 2024-04-10 | 2024-04-15 | 5 | Project Team, Project Manager | 0 | 12